## Sheet2
Three-Year Watershed Implementation Priorities - Puget Sound Salmon Recovery Plan
WRIA 9 Habitat Work Schedule for Green/Duwamish and Central Puget Sound Watershed
[10 empty] | 2008 |  | 2009 |  | 2010 |  |  | For Habitat projects (see key for categories)
Priority Tier | Primary Limiting Factors Addressed | Action Name and Description | Likely sponsor | Project, program, HP # | Total cost of first three years/phases | SRFB | KCD | ERP | Other Fund Sources | Year 2 Scope | Year 2 Cost | Year 3 Scope | Year 3 Cost | Year 4 Scope | Year 4 Cost | Likely end date | Acquisition | Restoration type, if applicable | Location w/in watershed | Performance
Capital Projects
Duwamish Subwatershed: Enlarge Duwamish estuarine transition zone habitat by expanding shallow water and slow water areas, and expand/enhance the estuary, particularly vegetated shallow subtidal and intertidal habitats and brackish marshes. VSP perameters for this subwatershed focus on productivity.
1 | 2,5 | North Wind's Weir Shallow Water Habitat Rehabilitation at RM 6.3: Create two acres of off-channel, shallow water habitat in the transition zone | King County | Project, DUW-10 | 2145000 |  |  |  | King County; US ACOE | Construction | 1975000 | Monitoring/Adaptive Management | 85000 | Monitoring/Adaptive Management | 85000 | 2008 | AR, R | E | Esturaine | 2 ac
1 | 2,5 | Shallow Water Habitat Creation: Creation of approximately 0.36 acre of nearshore habitat including a new cove and 2.1 acres of vegetated buffer adjacent to the river at City Light South at RM 5.2 (left bank) as part of mitigation by City of Seattle | Seattle | Project, DUW-11 | Habitat project costs to be determined | n/a | n/a | Funding will come from off-site mitigation for impacts of construction at Joint Training Facility on Hamm Creek |  | Construction | [5 empty] | 2008 | R | E | Esturaine | 2.1 ac
2 | 2,5 | Duwamish Gardens Shallow Water Habitat Creation at RM 7.0: Phase I: Acquire 2.2 acres of upland; Phase II: Create shallow water off channel habitat | Tukwila | Project, DUW-7 | Phase I (acquisition): $1,700,000 | $311,000 (2006) | $15,000 (2006); PENDING: KCD $200,000 (2007) |  | APPROVED: CFT: $350,000 (2006); City of Tukwila: $50,000 (2006); PENDING: ALEA: $195,000 (2006); City of Tukwila (2007) $50,000 | Complete acquisition | 1700000 | Design, engineering, permitting | 200000 | Archeological data recovery | 100000 | 2011 | AR, R | E | Esturaine | 2.2 ac
3 | 2,5 | Shallow Water Habitat Creation at RM 7.0-5.5: Create a minimum of 20 acres of new off-channel shallow water/marsh habitat with associated riparian vegetation; Restore 1 acre upstream of RM 5.5 | Tukwila | Project, DUW-7 | 1500000 |  |  |  | CFT, ALEA,City of Tukwila, KCD | Feasibility/Acquisition | 1300000 | Design, engineering, permitting | 100000 | Complete design, engineering, permitting | 100000 | 2011 | AR, R | E | Esturaine | 1 ac
3 | 1,5 | Bank Restoration and Revetment Setback at RM 6.6-5.5: Set back and restore the river bank; Combination of 3 projects to restore 1 mile bank layback, revegetation RM 4.7-7.0 | Tukwila & King County | Project, DUW-7, 9, 11 | 500000 |  |  |  | CFT, ALEA,City of Tukwila, KCD | Feasibility, negotiation with property owner, design and permitting | 150000 | LWD and materials purchase | 100000 | Placement and planting | 250000 | 2009 | R | E | Esturaine | 1 mi
3 | 2,5 | Shallow Water Habitat Creation at RM 7.0-5.5: Create a minimum of 20 acres of new off-channel shallow water/marsh habitat with associated riparian vegetation; Property Acquisition of 5 acres for 2010 restoration | Multiple stakeholders | Project, DUW-7 | 6100000 |  |  |  | CFT, ALEA,City of Tukwila, KCD | Property owner outreach | 60000 | Secure funding | 40000 | Complete acquisition | 6000000 | 2010 | AR, R | E | Esturaine | 5 ac
3 | 2,5 | Shallow Water Habitat Creation: Creation of shallow water habitat and shoreline restoration between RM 5.5-4.7 (and farther downstream) within the expected Lower Duwamish Superfund cleanup area | Multiple stakeholders | Project, DUW-11 | Unknown, TBD by Natural Resource Trustees | n/a (probably) | n/a (probably) | Funding will for the most part come from Natural Resource Damages |  | Actions will be scheduled by Natural Resource Trustees and/or potentially responsible parties | [5 empty] | n/a | R | E | Esturaine | 0.8 mi
|  | Subtotals |  |  | 11945000 | 311000 |  |  |  |  | 5185000 |  | 525000 |  | 6535000
Lower Green River Subwatershed: Protect/restore refuge, habitat complexity and connectivity for juvenile salmon over range of flow conditions and variety of locations. VSP perameters for this subwatershed focus on productivity.
1 | 1,3 | Riverview Park Restoration: Provide summer rearing habitat and high flow winter refuge through excavation of an off-channel area combined with placement of large woody debris and revegetation. | Kent | Project, LG-7 | 2020000 | $150,000 (2006) | $40,000 (2006) PENDING: $50,000 | PENDING: $1,163,000 | PENDING: Kent $617,000 | Complete Design & Permitting | 451200 | Construct Project | ? | Monitoring & Adaptive Management | 50000 |  | AR, R | I | Main | 0.13 mi
1 | 1,3 | Lower Green River Acquisition in Kent: Acquire three properties immediately upstream of the Mullen Slough confluence and demolish buildings on one. A subsequent phase would likely modify Frager Road and allow reconnection of the upland to the river. Also acquire the Koch property on the left bank downstream of Riverview Park. A subsequent phase would restore riparian habitat. | Kent (lead), King County, Green River Flood Control Zone District | Project, LG-7 | 1200000 | $975,085 (2003) |  |  | Kent $180,000; King County $25,000; Green River Flood Control Zone District $25,000 | Complete Acquisition | 1205000 | [5 empty] | AR, R | R | Main | ?
2 | 1,3 | Mill Creek Floodplain Wetland and Off-Channel Habitat Rehabilitation: Restore lower 0.3 miles of Mill Creek and adjacent segments of currently armored riverbank. | Kent | Project, LG-7 | 1500000 | $100,000 (2006) |  |  | APPROVED: CFT: $100,000 (2005 or 2006); City of Kent: $100,000 (2005 or 2006) | Complete Design & Permitting | 100000 | Construct Project | 1400000 | Monitoring & Adaptive Management |  | 2009 | AR, R | I, W | Main | 0.3 mi
3 | 1,3 | Briscoe Off Channel Habitat Rehabilitation between RM 16.1 and 15.8: Remove armoring on the Briscoe meander shoreline, excavate flood refugium for juvenil salmonid rearing habitat, install large woody debris, and plant native riparian vegetation. | Kent | Project, LG-12 | 1000000 | [8 empty] | Feasibility, design, permitting | 100000 | 2011 | R | R | Main | 0.3 mi
[17 empty] | R | R | Main
3 | 1,3 | Nelson Side-Channel Habitat Rehabilitation between RM 12.65 and 12.5: Restore historical flood refugia and off-channel rearing habitat on a riverside sheep pasture. | Tukwila | Project, LG-15 | 1500000 | [6 empty] | Feasibility | 40000 | Design, Permitting | 100000 | 2011 | R | R | Main | 0.15 mi
3 | 1,3 | Mainstem Maintenance: Boeing Levee Setback and Restoration between RM 18 and 17.1 to enable extensive habitat rehabilitation. | Kent & King County | Project, LG-10 | 650000 |  |  |  | GRFCZD, KCD, Kent, ACOE | Design Restoration Construction, Permitting | 150000 | Construction | 1500000 | Complete Construction | 1500000 |  | R | R | Main | 0.9 mi
|  | Subtotals |  |  | 7870000 | 1225085 |  |  |  |  | 1906200 |  | 2940000 |  | 1750000
Nearshore Subwatershed: Protect, restore, or rehabilitate: sediment transport processes by reconnecting sediment sources and removing shoreline armoring; pocket estuaries, lagoons, and spits; and sediment quality, particularly in Elliott Bay. VSP perameters for this subwatershed focus on productivity.
1 | 2,3 | Olympic Sculpture Park Tidal Embayment and Shallow Water Habitat Rehabilitation: Create a 0.64 acre embayment at the northern end of the Elliott Bay seawall and an approximately 800 foot long and 15 foot wide habitat bench between Pier 70 and Myrtle Edwards Park. CONSTRUCTION COMPLETE | Seattle | Project, NS-3 | 3114000 |  |  |  | Estuary and Salmon Restoration Program $77,712; Estuary and Salmon Restoration $35,500; King Conservation District (post-construction monitoring) $83,827 | Monitoring/Adaptive Management | 25000 | Monitoring/Adaptive Management | 25000 | Monitoring/Adaptive Management | 25000 | 2006 | R | M | Marine | 0.64 ac
2 | 2,3 | Burien Seahurst Park Shoreline Restoration, Phase II: Continue shoreline restoration actions conducted in southern portion of Seahurst Park in Burien by removing a portion of shoreline armoring in the central area of the park, restoring natural beach slopes, and adding riparian vegetation. | Burien | Project, NS-5 | ??? |  |  |  | Burien, IAC, PSAW |  |  | Feasibility | 40000 | Design, engineering, permitting | 100000 | Const. in 2011 | AR, R | M | Marine | ?
2 | 2,3 | Beaconsfield-On-The-Sound: Feeder Bluff Protection and Restoration of Beach Feeding Processes in Normandy Park: Purchase and restore one of the last major privately-held undeveloped feeder bluffs along the mainland marine shoreline. | Normandy Park | Project, NS-11 | 500000 | $50,873 (2005-2006); $100,000 (2006) |  |  | Cascade Land Conservancy $2,977 (2005) and $64,500 (2006); Normandy Park $6,000 (2005) | Feasibility, Technical Design | 100000 | Acquisition | 150000 | Construction | 250000 |  | AR, R | M | Marine | 1,000 ft
3 | 2,3 | Functioning Nearshore Habitat Protection: Protect site with high habitat resource value - Foss Property | Normandy Park | Project NS-17 | Adequate funding secured |  |  |  | Estuary and Salmon Restoration Program $65,000 | Acquisition | 160000 | Education and stewardship scope |  | Education and stewardship scope |  | 2008 | AP | M | Marine | ?
2 | 2,3 | Functioning Nearshore Habitat Protection: Protect site with high habitat resource value - Camp Kilworth. Most of this 25 acre parcel is forested upland and will serve as park. Nearshore is high quality and requires no restoration. | Federal Way | New project | 3116000 |  |  |  | Washington Wildlife & Recreation Program $1,000,000; Conservation Futures $400,000; City of Federal Way $1,016,000; TBD $700,000 | Acquisition | 3116000 |  |  |  |  | 2008 | AP | M | Marine | 2.5 ac
1 | 2,3 | Ellis Creek Saltmarsh Protection and Restoration on Vashon Island: Acquire and restore salmonid-accessible saltmarsh and riparian land at the mouth of Ellis Creek on Tramp Habor on the east side of Vashon Island. CONSTRUCTION SUMMER 2007 | King County | Project, NS-10 | 348000 | $189,438 (2006) |  |  | CFT, King County ($40,000), KCD | Monitoring/Adaptive Management | 5000 | Monitoring/Adaptive Management | 5000 | Monitoring/Adaptive Management | 5000 | 2007 | AP | M | Marine | 3.13 ac
1 | 2,3 | Functioning Nearshore Habitat Protection on Vashon/Maury Island: Protect sites with high habitat resource values - Lost Lake | King County | Project, NS-17 | Adequate funding secured |  |  |  | Conservation Futures, NOAA | TO BE COMPLETED 2007 | [5 empty] | 2007 | AP | M | Marine | ?
1 | 2,3 | Functioning Nearshore Habitat Protection on Vashon/Maury Island: Protect sites with high habitat resource values - Maury Island Marine Park | King County | Project, NS-17 | Adequate funding secured |  |  |  | Conservation Futures, NOAA | TO BE COMPLETED 2007 | [5 empty] | 2007 | AP | M | Marine | ?
1 | 2,3 | Functioning Nearshore Habitat Protection on Vashon/Maury Island: Protect sites with high habitat resource values - Inspiration Pt | King County | Project, NS-17 | Adequate funding secured |  |  |  | Conservation Futures, NOAA | TO BE COMPLETED 2007 | [5 empty] | 2007 | AP | M | Marine | ?
1 | 2,3 | Functioning Nearshore Habitat Protection on Vashon/Maury Island: Protect sites with high habitat resource values - Pt. Robinson | King County | Project, NS-17 | Adequate funding secured |  |  |  | Conservation Futures, NOAA | Acquisition | [5 empty] | 2008 | AP | M | Marine | ?
1 | 2,3 | Functioning Nearshore Habitat Protection on Vashon/Maury Island: Protect sites with high habitat resource values - Dockton | King County | Project, NS-17 | Adequate funding secured |  |  |  | Conservation Futures, NOAA | Acquisition | [5 empty] | 2008 | AP | M | Marine | ?
1 | 2,3 | Functioning Nearshore Habitat Protection on Vashon/Maury Island: Protect sites with high habitat resource values - Neill Pt | King County | Project, NS-17 | Adequate funding secured |  |  |  | Conservation Futures, NOAA | Acquisition | [5 empty] | 2008 | AP | M | Marine | ?
1 | 2,3 | Functioning Nearshore Habitat Protection on Vashon/Maury Island: Protect sites with high habitat resource values - Manzanita | King County | Project, NS-17 | Adequate funding secured |  |  |  | Conservation Futures, NOAA | Acquisition | [5 empty] | 2008 | AP | M | Marine | ?
1 | 2,3 | Functioning Nearshore Habitat Protection on Vashon/Maury Island: Protect sites with high habitat resource values - Northall (Piner West) | King County | Project NS-17 | Adequate funding secured |  |  |  | Conservation Futures, NOAA | Acquisition | [5 empty] | 2008 | AP | M | Marine | ?
1 | 2,3 | Functioning Nearshore Habitat Protection on Vashon/Maury Island: Protect sites with high habitat resource values - Raab's Lagoon Pocket Estuary | King County | Project, NS-17 | Adequate funding secured |  |  |  | Conservation Futures, NOAA | Acquisition | [5 empty] | 2008 | AP | M | Marine | ?
3 | 2,3 | Evaluate How to Improve Habitat Value of Raab's Lagoon/Pocket Estuary on Maury Island: Work with property owner and neighbors to identify ways to improve habitat. | King County | Project, NS-14 | Costs not available | [11 empty] | R | M | Marine | ?
3 | 2,3 | Functioning Nearshore Habitat Protection on Vashon/Maury Island: Protect sites with high habitat resource values - Pt. Heyer Drift Cell | King County | Project, NS-17 | ??? | [10 empty] | 2008 | AP | M | Marine | ?
3 | 2,3 | Functioning Nearshore Habitat Protection on Vashon/Maury Island: Protect sites with high habitat resource values - Christensen Creek This project also will require restoration in a subsequent phase. | King County | Project, NS-17 | ??? | [11 empty] | AP | M | Marine | ?
3 | 2,3 | Camp Sealth Fish Passage Improvements on Vashon Island: Improve fish passage and improve conditions in pocket estuaries. | King County | Project, NS-9 | $100,000 - $200,000 | [11 empty] | R | M | Marine | ?
3 | 2,3 | Mileta Creek Fish Passage Improvements on Vashon Island: Improve fish passage and improve conditions in pocket estuaries. | King County | Project, NS-9 | $100,000 - $200,000 | [11 empty] | R | M | Marine | ?
3 | 2,3 | Ellisport Creek Fish Passage Improvements on Vashon Island: Improve fish passage, beach condition, and cleanup hydrocarbons. This is a two phase project: 1) acquisition and 2) cleanup. | King County and/or Vashon-Maury Island Land Trust | Project, NS-9 | Acquisition $20,000 Cleanup $500,000 Culvert replacement $500,000 |  |  |  |  | Acquisition cost determined |  | Acquisition |  |  |  |  | R | M | Marine | ?
3 | 2,3 | Sandford Point Feeder Bluff Restoration on Vashon Island: Remove derelict bulkhead in front of feeder bluff. | King County | Project, NS-18 | 195000 | [11 empty] | R | M | Marine | ?
3 | 2,3 | Dockton Road Removal and Feeder Bluff Restoration on Vashon Island: Remove road and intertidal fill. Acquire upland properties if threatened by erosion. Project depends on Roads deciding to abandon the road. | King County Roads Division | Project, NS -17 and NS-19 | [12 empty] | R | M | Marine | ?
|  | Subtotals |  |  | $8,493,000 - $8,693,000 | [5 empty] | 3406000 |  | 215000 |  | 375000
Middle Green River Subwatershed: Protect/restore habitat that provides refuge and habitat complexity for juvenile salmon over a range of flow conditions and a variety of locations; enhance natural sediment recruitment by reconnecting sediment sources to river; protect and restore spawning and rearing habitat in lower Newaukum and Soos Creeks; maintain regional groundwater recharge and base flows to mainstem Green River.
3 | 1,2 | Flaming Geyser Floodplain Reconnection, Side Channel Connection and Habitat Restoration between RM 45.1 and RM 44.3: Phase 1 Side Channel Connection - Excavate a connection between the wall-based side channel inlet and the mainstem and construct logjams to reinstate channel migration. | King County | Project, MG-3 | 1100000 | 150000 |  |  | King County, State Parks, IAC, | Feasibility & Design | 150000 | Construction | 900000 |  |  | 2009 | R | I | Main | 0.8 mi
3 | 1,3 | Flaming Geyser Side Channel Construction, Floodplain Reconnection near RM 44: Phase 2 - Construct a side channel to increase the amount of off-channel habitat near river mile 44. | King County | Project, MG-4 | 100000 | [8 empty] | Feasibility & Design | 100000 |  | R | I | Main | ?
3 | 1,3 | Newaukum Creek Corridor Restoration Between Creek Miles 0.0 and 14.3: Restore process-based ecological functions that include wetland and riparian restoration on the Enumclaw Plateau. Early phases. | King County | Project, MG-6 | 1075000 |  |  |  | King County, ACOE, | Feasibility & Design | 75000 | Begin Construction | 500000 | Construction | 500000 |  | R | I | Main | 14.3 mi
3 | 1,3 | Newaukum Creek Mouth Restoration Between Creek Miles 0.0 and 4.3: Place large woody debris and plant native trees along the lower 4.3 miles of the creek, and reconfigure the lower 1,800 feet of the creek near the mouth. | King County | Project, MG-8 | 1175000 | $788,581 (2004) |  |  | King County, ACOE | Design & Permitting | 100000 | Construction | 1075000 | Monitoring/Adaptive Management |  |  | R | I | Main | 4.3 mi
3 | 1,3 | Lones Levee Removal near RM 38: Restore natural channel migration processes, consistent with current flow regimes of the Green River by removing Lones Levee at river mile 38. | King County | Project, MG-9 | 3000000 |  |  |  | SRFB Round 5, 2004: $788,581; King County, ACOE | Design & Permitting | 100000 | Design & Permitting | 100000 | Construction | 2800000 | 2010 | R | I | Main | ?
2 | 1,3 | Setback and Removal of Fenster and Pautzke Levees to Reconnect the Floodplain and Allow Channel Migration near RM 32: Fenster Levee Phase IA - Remove levees, lower the elevation of terraces and construct engineered logjams to reinstate floodplain connectivity and channel migration. | Auburn, King County | Project, MG-18 | 1400000 | $675,900 (2005-2006) |  |  | Green River Flood Control Zone District $90,000; City of Auburn $33,000 | Construction | 1225000 | Monitoring/Adaptive Management | 75000 | Monitoring/Adaptive Management | 75000 | 2008 | AR,R | I | Main | ?
3 | 1,3 | Setback and Removal of Fenster and Pautzke Levees to Reconnect the Floodplain and Allow Channel Migration near RM 32: Fenster Levee Phase IB - Remove levees, lower the elevation of terraces and construct engineered logjams to reinstate floodplain connectivity and channel migration. | Auburn, King County | Project, MG-18 | $600,000 - $800,000 | [6 empty] | Design & Permitting | 150000 | Construction | 650000 | 2010 | AR,R | I | Main | ?
3 | 1,3 | Setback and Removal of Fenster and Pautzke Levees to Reconnect the Floodplain and Allow Channel Migration near RM 32: Pautzke Levee - Remove levees, lower the elevation of terraces and construct engineered logjams to reinstate floodplain connectivity and channel migration. Phases A - E. | King County | Project, MG-18 | 3500000 | [6 empty] | Design & Permitting | 100000 | Construction | 3400000 |  | AR,R | I | Main | ?
2 | 1,3 | Big Spring Creek Restoration: Construct new stream channel to replace ditch. Connect coldwater springs to Newaukum Creek. | King County | Project, MG-7 | 1194590 |  |  |  |  | Construction | [5 empty] | 2008 | R | I | Main | ?
|  | Subtotals |  |  | $13,144,590 - $13,344,590 | 150000 |  |  |  |  | 1650000 |  | 2900000 |  | 7525000
|  | Totals |  |  | $41,452,590 - $41,852,590 | 1686085 |  |  |  |  | 12147200 |  | 6580000 |  | 16185000
Programs and Key Actions-Not Prioritized
|  | Lead entity coordination | Lead entity | Program | 225000 |  |  |  |  | Staffing (1 FTE) | 75000 | Staffing (1 FTE) | 75000 | Staffing (1 FTE) | 75000 | Ongoing
|  | Adaptive management and monitoring | Multiple stakeholders | Program | 600000 |  |  |  |  | Staffing (3 FTEs) | 200000 | Staffing (3 FTEs) | 200000 | Staffing (3 FTEs) | 200000 | Ongoing
|  | Nearshore Habitat Toolbox | King County | Program, N-1 | 250000 |  |  |  |  | feasibility | 20000 | design, permits, contract | 40000 | construction | 190000
|  | Create incentives Program to Remove Failing Septic Systems on Vashon/Maury Island | King County | Program, N-4
|  | Project Management and Public Outreach | WRIA Staff
|  | Stewardship & Educational Outreach | WRIA Staff
|  | Water Conservation Incentive Programs | Multiple stakeholders | Program, WW-2
|  | Work with jurisdictions and Department of Ecology to support a Shorelines Exemption for properties affected by salmon habitat restoration projects that would relocate the location of the ordinary high water mark. | Multiple stakeholders | Policy IN2
|  | Promote Plantive of Native Trees | Multiple stakeholders | WW-5
|  | Develop a Coordinated Acquisition Program for Natural Areas | King County | WW-15
|  | Increase/Expand Natural Yard Care Programs | Multiple stakeholders | WW-3,4
|  | Conduct Shoreline Stewardship Workshops and Outreach - Beach/Bluff Educational Programs, including HPA education to agency staff and citizens. | Multiple stakeholders | WW-1
|  | Create Soft Armoring Tech Assist/Cost Share | King County | Program, N-2
|  | Citizen Volunteer Forage Fish Monitoring Program | Multiple stakeholders | Program N-5
|  | Promote Better Volunteer Carwash Practices | Multiple stakeholders | Program, WW-6
|  | Increase Public Awareness about What Healthy Streams and Rivers Look Like and How to Enjoy Recreating on Them | Multiple stakeholders | Program, WW-7
|  | Expand/Improve Incentives Programs | Multiple stakeholders | WW-11
|  | Increase Use of Low Impact Development and Porous Concrete | Multiple stakeholders | Program, WW-13
|  | Develop Salmon Restoration Tools Consistent with Agricultural Land Uses | Multiple stakeholders | Program, WW-16
|  | Work with Co-Managers to integrate Hatchery & Harvest Practices with Habitat Plan Objectives | Multiple stakeholders
|  | Olympic sculpture park post construction monitoring. | City of Seattle |  | $77,000 WDFW grant, SRFB, KCD
|  | Water supply coordination per DOE/EPA Watershed assistance grant | Multiple stakeholders |  | 50000